## W1
PROJECT REPORT
Group | CoffeeShop Team
Week | 3/3/2024 - 9/3/2024
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Front-end | All Team | Completed
| Coding | All Team | In Progress
| Update Database | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Coding CRUD Order | Thien | 13/3/2025
| Coding CRUD Payment | Minh | 13/3/2025
| Coding CRUD Authentication | My | 13/3/2025
| Coding CRUD Workshift | Thinh | 13/3/2025
| Coding CRUD Product | Tuan | 13/3/2025
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes