## W1
PROJECT REPORT
Group | CafeHub Team
Week | 13/1/2024 - 18/1/2024
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Create SRS for Mock Project | All Team | In Progress | Draw Usecase Diagram for Admin Role - Menu Management + Storage
| Meeting for SRS |  | Completed | Meeting to assign task for team's member for create SRS document
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Review and update SRS | All Team | 21/1/2024
| Define the database for the project | All Team | 23/1/2024 | Decide database type and structure
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes