## W1
PROJECT REPORT
Group | Coffee shop management and sales website
Week | 11/1/2025 - 18/1/2025
I. Status Report
# | Project Task | In-charge | Status | Notes (Work Item in Details)
| Hoàn thành Use case diagram và họp để cùng sửa lại các Use cases | All Team | Completed
II. Project Issues
# | Project Issue | Owner | Status | Notes (Solution, Suggestion, etc.)
III. Next Week Plan
# | Project Work Item | In-charge | Deadline | Notes (Task Details, etc.)
| Complete SRS | All Team | 21/01/2025
| Review and Update SRS | All Team |  | Hoàn thành sau kì nghỉ Tết
IV. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Date | Notes